## Slide 1: Sprint retrospective
Team A

## Slide 2: Stories
We decided to commit for 16 and we completed all of them.
The stories we committed for have a total score of 57 points, while we managed to complete all of them.

## Slide 3: Tasks
In addition to the stories, we also took another setup task related both to them and to establish more ground for future stories.
The tasks had a size of 13 points, all completed.

## Slide 4: Estimations and errors
We had about 60 person hours estimated in our tasks.
The estimation was about right when we added other stories, since we managed to finish everything earlier then expected.

## Slide 5: Estimations: burndown chart
Chart: Burndown chart
| 43817 | 43819 | 43826 | 43832 | 43834 | 43837 | 43838 | 43840 | 43841
Points left | 70 | 55 | 50 | 29 | 23 | 17 | 15 | 8 | 0
Estimated points left | 70 | 0

## Slide 6: What we learned
Improved planification and routing
Story points get heavily cut using a well-done setup
Code redundancy is really bad and we should avoid it as much as possible

## Slide 7: What we are proud of
Improved website
Very low technical debt, with the exception of a small redundant portion of code

## Slide 8: Possible improvements
More communication (again)
Even more testing can be done
We really miss regression testing when files get messed up. We assume files never get messed up, yet sometimes it happens and we should all react to this evenience.

## Slide 9: Thank you!