## Slide 1: Sprint retrospective
Team A

## Slide 2: Stories
We decided to commit for 3 stories for few points, but we managed to complete only two.
The stories we committed for have a total score of 21 points, while we managed to complete 8 of those.

## Slide 3: Tasks
Since the stories committed were few and we had many adjustments to make, we decided to make more documentation about the flow of the website.
When the documentation was completed, we added a 21-points task we had to commit, presenting a prototype of the website mainly for the parent view, adding a few pages for the parent and the office administrator.

## Slide 4: Estimations and errors
We had about 60 person hours estimated in our tasks, as the time before.
Because of Docker issues and internal changes, the work was done in about 76 person hours.

## Slide 5: Estimations: burndown chart
The burndown chart is updated to the times we decided the tasks were considered “done”: this is a new process we are starting to establish, that is considering something “done” with the team consent.
Chart: 
| 43789 | 43799 | 43801 | 43802
Points left | 33 | 28 | 13 | 0
Estimated points left | 34 | 0

## Slide 6: What we learned
Sometimes a larger setup is needed to create the basics of the project
Communication is one of the keys to success
Advanced JS, with creation of modules
How to deal with technical difficulties

## Slide 7: What we are proud of
Improving our workflow
We delivered more while “doing less”, and set up the future project development in a better way

## Slide 8: Possible improvements
More structure can be added to the project
We should challenge us even more from now on, being able to take more stories

## Slide 9: Thank you!