## Slide 1: Sprint retrospective
Team A

## Slide 2: Stories
We decided to commit for 5 out of 7 stories, since the latest two had so many points assigned that they would have doubled the work.
The stories we committed for have a total score of 13 points.

## Slide 3: Tasks
Each story was divided in 4 or 5 tasks, each one with different length.
Each task has an average estimated duration of 40/50 minutes. The overall.
The setup was estimated having 5 points, lasting about 15 hours in total. This increased the average estimation to 1 hour per task.
The actual average time spent on each task was roughly 1:30 hours.
More details in our estimation can be found here.

## Slide 4: Estimations and errors
We had about 32 hours estimated in our tasks. We knew we could make errors, so we decided not to overdo.
This turned out to be the right decision, since we spent 38 hours in total implementing the stories.
The error ratio resulting is 38/32 hours = 1.1875

## Slide 5: Stories and estimations: points
We only had 3 and 2 points stories.
For the 3 point ones, the total average time spent on each was 4:30 hours.
For the 2 point ones, it was also 4:30 hours.
This is probably due to an estimation error in one of the 2-point stories, since it lasted the same time as the longest of the 3-point ones.

## Slide 6: Stories and estimations: time
Since the error in calculating the points, we have a paradox: the longest stories in time (5 hours) have an average of 2.5 points, while shorter ones have an average of 3 points.
The only story lasting 4:30 hours has an average of 3 points, while the ones lasting 4 hours have an average of 2.5 points.

## Slide 7: What we learned
Estimation is not easy, even with poker
The team may have different visions from you, and many coding styles differ from each other because of this; also, because of this, the code should have meaningful variable names and comments.
We should have divided our tasks better.

## Slide 8: What we are proud of
Buttons. They are big, Gertrude is happy.
Modularity: the code is really flexible and allows us even to use it in a rough way, sacrificing little performance to improve developing time
An off-by-1 error that no one noticed.

## Slide 9: Thank you!