## Slide 1: Sprint retrospective
Team A

## Slide 2: Stories
We decided to commit for 5 stories, but we managed to complete only two.
The stories we committed for have a total score of 26 points, while we managed to complete 12 of those.

## Slide 3: Tasks
Each story was divided in 3 to 9 tasks, also trying experimenting with what we learned in class.
The setup was estimated having 8 points, lasting about 40 person hours in total.
Some task didn’t end because we decided we needed to learn more about Node, so one is still open and will be closed later.

## Slide 4: Estimations and errors
We had about 60 hours estimated in our tasks, but we later acknowledged that, using a new technology, it would have been difficult to complete everything within time.
We found that the stories were not the main issue, but the setup was: Docker had different problems on each PC and we spent at least 16 person hours solving those issues.

## Slide 5: Stories and estimations: points
We only had 3 and 2 points stories.
For the 3 point ones, the total average time spent on each was 4:30 hours.
For the 2 point ones, it was also 4:30 hours.
This is probably due to an estimation error in one of the 2-point stories, since it lasted the same time as the longest of the 3-point ones.

## Slide 6: Stories and estimations: points
In the end, what we found out is that 1 point is equal to 38/18 ~= 2 hours.

## Slide 7: Estimations: burndown chart
The burndown chart shows our issues, first struggling with the setup and then recognising that the points we committed were too many.
Overall we managed to complete about half of the points we committed, including the setup.
Chart: 
| 43774 | 43778 | 43779 | 43782 | 43784 | 43785 | 43786 | 43787
Points left | 34 | 29 | 26 | 24 | 19 | 19 | 18 | 18
Estimated points left | 34 | 0

## Slide 8: What we learned
Do not underestimate setup times
We should work more together in the next sprints
We should have divided our tasks better
New technologies take a lot of time to be learned
The former frame of mind didn’t work for such a large project, and we are moving to what we think to be a better one

## Slide 9: What we are proud of
We experimented with something new: NodeJS, PUG as a view engine, Docker as a host for our application
Thanks to NodeJS, we managed to implement a good MVC pattern
Thanks to PUG, we learned to automate the page creation, using a single .pug file with different parameters to generate two different HTML pages

## Slide 10: Thank you!